## Přehled CZ
UCO3001 — CZ CTMS Visits Overview ¦ 2026-04-27
Site | Investigátor | SQV | SIV | IMV Completed | IMV Scheduled | IMV Planned | COV | Poslední vizita Datum | Poslední vizita Typ | Příští vizita Datum | Příští vizita Typ | Celkem vizit
DD5-CZ10001 | Matej Falc | Completed | Completed | 2 | 1 | 0 | — | 2026-04-09 | IMV2 | 2026-06-01 | IMV3 | 5
DD5-CZ10003 | Leksa Vaclav | Completed | Completed | 0 | 0 | 0 | — | 2025-12-05 | SIV |  | — | 2
DD5-CZ10006 | Michal Konecny | Completed | Completed | 1 | 0 | 0 | — | 2026-03-12 | IMV1 |  | — | 3
DD5-CZ10009 | Jiri Pumprla | Completed | Completed | 0 | 0 | 1 | — | 2025-12-11 | SIV | 2026-02-09 | IMV1 | 3
DD5-CZ10010 | Nabil El Lababidi | Completed | Completed | 0 | 0 | 0 | — | 2026-04-13 | SIV |  | — | 2
DD5-CZ10012 | Stefan Konecny | Completed | Completed | 1 | 0 | 0 | — | 2026-03-30 | IMV1 |  | — | 3
DD5-CZ10013 | David Stepek | Completed | Completed | 1 | 0 | 0 | — | 2026-03-23 | IMV1 |  | — | 3
DD5-CZ10015 | Jan Matous | Completed | Completed | 1 | 0 | 0 | — | 2026-04-15 | IMV1 |  | — | 3
DD5-CZ10016 | Robert Mudr | Completed | Completed | 1 | 0 | 0 | — | 2026-04-15 | IMV1 |  | — | 3
DD5-CZ10020 | Lucie Gonsorcikova | Completed | Completed | 0 | 1 | 0 | — | 2026-03-25 | SIV |  | — | 3
DD5-CZ10021 | Martin Bortlik | Completed | Completed | 2 | 0 | 0 | — | 2026-04-22 | IMV2 |  | — | 4
DD5-CZ10022 | Petr Hrabak | Completed | Completed | 3 | 1 | 0 | — | 2026-03-18 | IMV3 | 2026-08-27 | IMV4 | 6

## Detail CZ
UCO3001 — CZ CTMS Visits — Detail ¦ 2026-04-27
Site | Investigátor | CRA (Submitter) | Ref | Název vizity | Category | Sub Category | Status | Due Date | Window Start | Cutoff Date | Completed Date | Typ vizity
DD5-CZ10001 | Matej Falc | Placha, Lenka | SQV | Qualification Visit | Qualification Visit | Within the plan | Completed | 2025-05-03 | 2025-05-03 | 2025-05-03 | 2025-05-16 | Remote
DD5-CZ10001 | Matej Falc | Ruiz Kajtarova, Agnesa | SIV | Site Initiation | Initiation Visit | Within the plan | Completed | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-22 | On Site
DD5-CZ10001 | Matej Falc | Ruiz Kajtarova, Agnesa | IMV1 | Monitoring Visit 1 | Monitoring Visit |  | Completed | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-05 | On Site
DD5-CZ10001 | Matej Falc | Ruiz Kajtarova, Agnesa | IMV2 | Monitoring Visit 2 | Monitoring Visit |  | Completed | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-09 | On Site
DD5-CZ10001 | Matej Falc |  | IMV3 | Monitoring Visit 3 | Monitoring Visit |  | Scheduled | 2026-06-01 | 2026-06-01 | 2026-06-01
DD5-CZ10003 | Leksa Vaclav | Pavlasova, Zaneta | SQV | Qualification Visit | Qualification Visit |  | Completed | 2025-05-03 | 2025-05-03 | 2025-05-03 | 2025-05-26 | Remote
DD5-CZ10003 | Leksa Vaclav | Ruiz Kajtarova, Agnesa | SIV | Site Initiation | Initiation Visit | Within the plan | Completed | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2025-12-05 | On Site
DD5-CZ10006 | Michal Konecny | Cetkovská, Vladimíra | SQV | Qualification Visit | Qualification Visit |  | Completed | 2025-05-03 | 2025-05-03 | 2025-05-03 | 2025-05-27 | On Site
DD5-CZ10006 | Michal Konecny | Maxa, Daniel | SIV | Site Initiation | Initiation Visit |  | Completed | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-12 | On Site
DD5-CZ10006 | Michal Konecny | Maxa, Daniel | IMV1 | Monitoring Visit 1 | Monitoring Visit | Within the plan | Completed | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | On Site
DD5-CZ10009 | Jiri Pumprla | Cetkovská, Vladimíra | SQV | Qualification Visit | Qualification Visit |  | Completed | 2025-05-03 | 2025-05-03 | 2025-05-03 | 2025-05-21 | On Site
DD5-CZ10009 | Jiri Pumprla | Sába, Martina | SIV | Site Initiation | Initiation Visit | Within the plan | Completed | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-11 | On Site
DD5-CZ10009 | Jiri Pumprla |  | IMV1 | Monitoring Visit 1 | Monitoring Visit | Within the plan | Planned | 2026-02-09 | 2026-02-09 | 2026-02-09
DD5-CZ10010 | Nabil El Lababidi | Dufkova, Iveta | SQV | Qualification Visit | Qualification Visit | Within the plan | Completed | 2025-05-03 | 2025-05-03 | 2025-05-03 | 2025-05-26 | On Site
DD5-CZ10010 | Nabil El Lababidi | Sába, Martina | SIV | Site Initiation | Initiation Visit | Outside the plan | Completed | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-04-13 | On Site
DD5-CZ10012 | Stefan Konecny | Pavlasova, Zaneta | SQV | Qualification Visit | Qualification Visit |  | Completed | 2025-05-03 | 2025-05-03 | 2025-05-03 | 2025-05-22 | Remote
DD5-CZ10012 | Stefan Konecny | Maxa, Daniel | SIV | Site Initiation | Initiation Visit |  | Completed | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-30 | On Site
DD5-CZ10012 | Stefan Konecny | Maxa, Daniel | IMV1 | Monitoring Visit 1 | Monitoring Visit | Within the plan | Completed | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-30 | On Site
DD5-CZ10013 | David Stepek | Placha, Lenka | SQV | Qualification Visit | Qualification Visit | Within the plan | Completed | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-13 | On Site
DD5-CZ10013 | David Stepek | Sába, Martina | SIV | Site Initiation | Initiation Visit | Within the plan | Completed | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-12 | On Site
DD5-CZ10013 | David Stepek | Sába, Martina | IMV1 | Monitoring Visit 1 | Monitoring Visit | Within the plan | Completed | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-23 | On Site
DD5-CZ10015 | Jan Matous | Dufkova, Iveta | SQV | Qualification Visit | Qualification Visit | Within the plan | Completed | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-21 | On Site
DD5-CZ10015 | Jan Matous | Ruiz Kajtarova, Agnesa | SIV | Site Initiation | Initiation Visit | Within the plan | Completed | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | On Site
DD5-CZ10015 | Jan Matous |  | IMV1 | Monitoring Visit 1 | Monitoring Visit |  | Completed | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-04-15
DD5-CZ10016 | Robert Mudr | Placha, Lenka | SQV | Qualification Visit | Qualification Visit | Within the plan | Completed | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-13 | On Site
DD5-CZ10016 | Robert Mudr | Maxa, Daniel | SIV | Site Initiation | Initiation Visit |  | Completed | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-27 | On Site
DD5-CZ10016 | Robert Mudr |  | IMV1 | Monitoring Visit 1 | Monitoring Visit | Within the plan | Completed | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-04-15
DD5-CZ10020 | Lucie Gonsorcikova | Placha, Lenka | SQV | Qualification Visit | Qualification Visit | Within the plan | Completed | 2025-05-13 | 2025-05-13 | 2025-05-13 |  | On Site
DD5-CZ10020 | Lucie Gonsorcikova | Sába, Martina | SIV | Site Initiation | Initiation Visit | Within the plan | Completed | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-03-25 | On Site
DD5-CZ10020 | Lucie Gonsorcikova |  | IMV1 | Monitoring Visit 1 | Monitoring Visit | Within the plan | Scheduled | 2026-03-17 | 2026-03-17 | 2026-03-17
DD5-CZ10021 | Martin Bortlik | Placha, Lenka | SQV | Qualification Visit | Qualification Visit | Within the plan | Completed | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-21 | Remote
DD5-CZ10021 | Martin Bortlik | Ruiz Kajtarova, Agnesa | SIV | Site Initiation | Initiation Visit | Within the plan | Completed | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-20 | On Site
DD5-CZ10021 | Martin Bortlik | Ruiz Kajtarova, Agnesa | IMV1 | Monitoring Visit 1 | Monitoring Visit |  | Completed | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-17 | On Site
DD5-CZ10021 | Martin Bortlik |  | IMV2 | Monitoring Visit 2 | Monitoring Visit |  | Completed | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-04-22
DD5-CZ10022 | Petr Hrabak | Maxa, Daniel | SQV | Qualification Visit | Qualification Visit |  | Completed | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-30 | On Site
DD5-CZ10022 | Petr Hrabak | Maxa, Daniel | SIV | Site Initiation | Initiation Visit | Within the plan | Completed | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2025-12-18 | On Site
DD5-CZ10022 | Petr Hrabak | Maxa, Daniel | IMV1 | Monitoring Visit 1 | Monitoring Visit |  | Completed | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-02-09 | On Site
DD5-CZ10022 | Petr Hrabak | Maxa, Daniel | IMV2 | Monitoring Visit 2 | Monitoring Visit | Within the plan | Completed | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-03-06 | On Site
DD5-CZ10022 | Petr Hrabak | Maxa, Daniel | IMV3 | Monitoring Visit 3 | Monitoring Visit | Within the plan | Completed | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-03-18 | On Site
DD5-CZ10022 | Petr Hrabak |  | IMV4 | Monitoring Visit 4 | Monitoring Visit | Within the plan | Scheduled | 2026-08-27 | 2026-08-27 | 2026-08-27

## Nadcházející vizity
UCO3001 — CZ — Nadcházející vizity (Scheduled + Planned) ¦ 2026-04-27
Due Date | Site | Investigátor | CRA | Ref | Název vizity | Category | Status | Window Start | Cutoff Date
2026-02-09 | DD5-CZ10009 | Jiri Pumprla |  | IMV1 | Monitoring Visit 1 | Monitoring Visit | Planned | 2026-02-09 | 2026-02-09
2026-03-17 | DD5-CZ10020 | Lucie Gonsorcikova |  | IMV1 | Monitoring Visit 1 | Monitoring Visit | Scheduled | 2026-03-17 | 2026-03-17
2026-06-01 | DD5-CZ10001 | Matej Falc |  | IMV3 | Monitoring Visit 3 | Monitoring Visit | Scheduled | 2026-06-01 | 2026-06-01
2026-08-27 | DD5-CZ10022 | Petr Hrabak |  | IMV4 | Monitoring Visit 4 | Monitoring Visit | Scheduled | 2026-08-27 | 2026-08-27

## Problémy
UCO3001 — CZ — Datové problémy k opravě v OneCTMS ¦ 2026-04-27
Site | Investigátor | CRA (Submitter) | Ref | Název vizity | Category | Status | Due Date | Completed Date | Důvod — co je potřeba opravit v OneCTMS